## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a researcher, I want to document the existing IVR system and understand its capabilities and limitations so that to support informed development. | SHOULD HAVE | Documentation research | Documentation Team | 3- Completed
Sprint 2 | Sprint 2 | US002 | As a Backend developer, I want to create the required APIendpoints, so that it can be helpful for proper dataflow and smooth operation. | MUST HAVE | APIs Ready | Backend Team | 3- Completed
Sprint 2 | Sprint 2 | US003 | As an AI developer, I want to integrate the system with NLU engine so that to enable users with accurate intent recognition. | MUST HAVE | Intent-Model | Backend Team | 3- Completed
Sprint 3 | Sprint 3 | US004 | As a frontend developer, I want to implement a responsive UI so that to to enhance usability and ensure better user experience. | MUST HAVE | Designs ready | Frontend Team | 3- Completed
Sprint 4 | Sprint 4 | US005 | As a devOps engineer, I want to integrate the entire system in a test environment so that to validate performance and demonstrate system reliability. | COULD HAVE | Frontend and Backend integration | Both frontend & Backend Team | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 54 | 3 | 4 | 6 | 4 | 7 | 2 | 2 | 6 | 2.5 | 4 | 1 | 4 | 3 | 4.5
SPRINT 1 BACKLOG
US001 | T1 | Analyze and document the architecture, call flow, and limitations of the current IVR system to support further integration and design decisions. | 2025-09-22 | 2025-10-06 | Development1 | Others | 3- Completed | 8 | Day 1: 2; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 1; Day 7: 1; Day 8: 1
US002 | T2 | Develop REST endpoints to process IVR events, route menu selections, and manage call state transitions. | 2025-10-07 | 2025-10-20 | Backend1 | Coding | 3- Completed | 11.5 | Day 2: 1; Day 4: 2; Day 5: 1; Day 6: 1; Day 8: 2; Day 9: 1.5; Day 10: 1; Day 13: 2
US003 | T3 | Integrate a speech-to-intent pipeline using NLU models to enable natural language input and intent mapping. | 2025-10-21 | 2025-11-03 | Backend2 | Coding | 3- Completed | 12 |  | 2 | 2 | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  | 1 | 1
US004 | T4 | Implement an adaptive frontend to display call states, menus, and voice interactions across devices. | 2025-11-04 | 2025-11-10 | Frontend1 | Design | 3- Completed | 11.5 | Day 3: 2; Day 5: 2; Day 6: 1; Day 8: 1; Day 10: 1; Day 12: 2; Day 14: 1.5
US005 | T5 | Deploy all modules into a test environment, validate system flow, and ensure interoperability across components. | 2025-11-11 | 2025-11-15 | Both Teams | Unit Test | 3- Completed | 11 | Day 1: 1; Day 3: 1; Day 5: 2; Day 7: 1; Day 8: 1; Day 10: 1; Day 12: 2; Day 14: 2
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Difficulty understanding complex legacy IVR flows | Discussed with mentor and documented simplified flow diagrams
Sprint 2 | Day 3 | Middleware not connecting properly with backend functions | Checked request/response format and fixed mapping issues
Sprint 2 | Day 4 | API calls not returning expected values | Added logs, fixed incorrect parameters, and retested endpoints
Sprint 3 | Day 2 | Voice flow responses not matching the designed prompts | Updated conversational intents and retuned dialogue logic
Sprint 4 | Day 1 | Frontend unable to fetch responses from backend | Enabled CORS and verified API routes in frontend

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-09-22 | 2025-10-05 | Documentation Team | Organizing legacy IVR documents into a structured format. | Relying on outdated or partial documentation. | Verifying requirements with functional stakeholders. | Reviewed legacy VXML scripts and mapped functional call states into structured documentation.
2 | 2 | 2025-10-06 | 2025-11-19 | Backend Team | Designing APIs with clear input/output schemas. | Writing tightly coupled logic inside endpoints. | Modularizing state logic for maintainability. | Implemented Flask APIs and state machine modules with proper routing.
3 | 2 | 2025-10-20 | 2025-11-03 | Backend Team | Designing fallback and clarification strategies. | Allowing uncertain intents to map automatically. | Testing with diverse accents and phrasing variations. | Integrated voice recognition mapping with intents.
4 | 3 | 2025-11-04 | 2025-11-17 | Frontend Team | Validating browser permissions for microphone access. | Hard-coding text messages inside components. | Improving "barge-in" for a more natural feel. | Implemented speech barge-in, typing animation, waveform indicator.
5 | 4 | 2025-11-18 | 2025-11-22 | Deployment | Performing integration tests after each build. | Changing configuration directly on the production server. | Testing all major call flows after each deployment iteration. | Enabled CORS rules, and deployed test environment for demo validation.